## Sheet1
| Project Task | Labour Hours | Labour Cost | Task Cost
1 | Design Breakout Board
1.1 | Schematic | 40 | 72800
1.2 | Placement + Layout | 40 | 72800
1.3 | Review | 20 | 36400
1.4 | Assembly + Dry Run tests | 40 | 72800
| Sub Total | 140 |  | 254800
2 | MVT Technique Testing
2.1 | MVT IP Core Vivado | 120 | 218400
2.2 | MVT Simulation | 40 | 72800
2.3 | DAC Calibration | 80 | 145600
2.4 | Testing and measurements | 160 | 291200
| Sub Total | 400 |  | 728000 |  | ~350 is approved. Roughly 194 hours | 194
| Total | 540 |  | 982800
| Task Breakdown | Date | Hours | Total
Phase 1 | Planning | 17-05-2024 | 8
|  | 20-05-2024 | 8
|  | 31-05-2024 | 8
|  | 03-06-2024 | 8
|  | 10-06-2024 | 8
|  | 14-06-2024 | 8 | 48
| Component Acquisition | 19,20,21-06-2024 | 24 | 24
| Hardware Assembly | 26,27,28-06-2024 | 24 | 24
| Software Startup | 11,12-07-2024 | 12 | 12
| Firmware Startup | 15,16,17-07-2024 | 24 | 24
| Task Breakdown | Date | Hours | Total |  | Counter for phase 2: | 253
Phase 2 | Initial planning | 29-10-2024 | 2 |  |  | Percentage used up: | 130.4%
|  | 30-10-2024 | 2
|  | 31-10-2024 | 3 | 7
| Firmware Project Setup | 06-11-2024 | 1
|  | 07-11-2024 | 2
|  | 08-11-2024 | 1 | 4
| Linux Setup | 19-11-2024 | 2
|  | 20-11-2024 | 2
|  | 21-11-2024 | 1 | 5
| Debug LEDs software file | 25-11-2024 | 3
|  | 28-11-2024 | 1 | 4
| Debug LEDs HW + tcl script | 03-12-2024 | 2
|  | 04-12-2024 | 3
|  | 05-12-2024 | 9 | 14 | full day
| I2C Block integration | 06-12-2024 | 2
|  | 07-12-2024 | 3 | 5
|  | 09-12-2024 | 2
| DAC Wiring + Testing | 10-12-2024 | 2
|  | 11-12-2024 | 10
|  | 12-12-2024 | 2
|  | 13-12-2024 | 2
|  | 14-12-2024 | 4
|  | 17-12-2024 | 2
|  | 18-12-2024 | 2
|  | 19-12-2024 | 2
|  | 20-12-2024 | 2
| Task Breakdown | Date | Hours | Total |  | Counter for phase 2 (2025): | 224
|  | 15 - 21 Sep | 40 |  |  | Assume total hours phase 2 : | 330
|  | 22 - 28 Sep | 32
|  | 29 Sep - 05 Okt | 40 |  |  | Hours left: | 106
|  | 06 - 12 Okt | 32 |  |  | Weeks: | 2.65
|  | 13 - 19 Okt | 40
|  | 20-26 Okt | 40