## Slide 1
Sadie, Adriaan
2025 – MVT Signal Acquisition with FPGA

## Slide 2: Technology Project - 2025 Multi-voltage thresholding (mVT) Signal acquisition with FPGA
  Tasks completed
  Tasks left
  Budget
  Timeline
  4. Motivation

## Slide 3: Technology Project: MVT with FPGA Tasks completed
Initial tasks complete Part of task 2.3 also completed | 

## Slide 4: Technology Project: MVT with FPGA Tasks completed
Tasks completed for phase 2: Hours used for phase 2: 69 Hours in initial budget for phase 2: 400 (~R728000) Hours initially approved for phase 2: ~194 (R350000) Total usage for phase 2 of initial budget: ~36% | 

## Slide 5: Technology Project: MVT with FPGA Tasks left
 | DACs need to be calibrated according to the LVDS inputs to the FPGA (will take longest time). MVT IP core needs to be connected to rest of firmware. Sample signals must be measured with MVT technique and confirmed to be correct.

## Slide 6: Technology Project: MVT with FPGA Budget
Remaining hours from initial budget for phase 2:
400 – 69 = 331 hours for remaining tasks
~R629000 @ R1900/hour

## Slide 7: Technology Project: MVT with FPGA Timeline / Schedule
Timeline
Technology projects consistently hold a lower priority compared to customer assignments.
Consequently, our intention is to utilize this as an interim task between ongoing work, with the goal of completion by 2025.
~50% time allocation for 2024/2025
Resources only from HE Group

## Slide 8: Technology Plan: MVT with FPGA motivation
Pros:
Cheaper alternative for ADCs
Simpler interface
Avoid obsolescence issues with highly specialised ADCs
Can be implemented on cheaper MPSoC FPGA devices
  Compared to expensive RFSoC with internal ADCs
Only external component is slow, cheap, and common DAC
Once-off calibration
Can be used for next iteration of MAW-400, if proven
Cons:
Each bit requires a differential input, therefore, 12-bit ADC uses 12 differential pairs.

## Slide 9: Technology Plan: MVT with FPGA References
Eliseev, D., et al. "An open-sorce IP-Core for Multi-Voltage Thresholding signal acquisition with FPGAs." Journal of Instrumentation 19.02 (2024): C02035.

## Slide 10
http://www.saabgroup.com
Thank You